## Sheet1
Schedule | Expected Completion Date | Final Date of Completion | Actual Completion Date | Due Date | Key
|  |  |  | 2024-11-15 | Ahead of Schedule
1. Requirement Analysis | 2024-11-07 | 2024-11-07 |  |  | Target Met
A. Requirements Traceability Matrix updated | 2024-11-06 | 2024-11-07 | 2024-11-07 |  | Target Missed
B. Test Schedule updated | 2024-11-06 | 2024-11-07 | 2024-11-07 |  | Target in Progress
C. Acceptance Criteria updated | 2024-11-06 | 2024-11-07 | 2024-11-07 |  | Document is Fluid
D. Test Results aggregated
E. Defect Reports aggregated
2. Test Planning | 2024-11-07 | 2024-11-07 |  | 2024-11-15
A. Automation Strategy | 2024-11-06 | 2024-11-07 | 2024-11-07
B. Software Requirements Specification updated | 2024-11-06 | 2024-11-07 | 2024-11-07
3. Test Case Development | 2024-11-10 | 2024-11-12 |  | 2024-11-15
A. Automated Test cases | 2024-11-10 | 2024-11-12
B. Test Data | 2024-11-10 | 2024-11-12
C. Setup | 2024-11-10 | 2024-11-12
4. Test Environment Setup | 2024-11-12 | 2024-11-13 |  | 2024-11-15
A. Test environement is configured | 2024-11-12 | 2024-11-12
B. Smoke tests all pass | 2024-11-12 | 2024-11-12
5. Test Execution | 2024-11-13 | 2024-11-14 |  | 2024-11-15
A. Automated Test cases are executed | 2024-11-13 | 2024-11-14
B. Defects are logged in Jira | 2024-11-13 | 2024-11-14
C. Test results are documented in Jira | 2024-11-13 | 2024-11-14
D. Test reports are made | 2024-11-13 | 2024-11-14
6. Test Cycle Closure | 2024-11-14 | 2024-11-14 |  | 2024-11-15
A. Test summary report is made | 2024-11-13 | 2024-11-14
B. Presentation | 2024-11-14 | 2024-11-14
C. Documentation updated | 2024-11-13 | 2024-11-14