## Sheet1
Test Plan
Objective: | To implement Quality Control on the Planetarium application with the use of Jira and automation testing. The goal is to build upon the first sprint to look for defects within the application and provide constructive and detailed feedback on user workability and experience.
Phases: | 1. Requirement Analysis | Deliverables: | Test Schedule | RTM | Acceptance Testing | Phase Completion date | 2024-11-07
| 2. Test Planning | Deliverables: | Test Strategy | SRS |  | Phase Completion date | 2024-11-07
| 3. Test Case Development | Deliverables: | Use Case documents | Test Data | Test Scenarios | Phase Completion date | 2024-11-12
| 4. Test Environment Setup | Deliverables: | Smoke Tests | Jira Reports |  | Phase Completion date | 2024-11-13
| 5. Test Execution | Deliverables: | Defects Report | Test result Document |  | Phase Completion date | 2024-11-14
| 6. Test Cycle Closure | Deliverables: | Test Summary Report | Presentation |  | Phase Completion date | 2024-11-14
Cost: | Null
Specifications: | A robust and detailed series of documentation that detail the applications functionality, workability, ease of use for the user, design, and structure. With the use of Jira reports are to be made that document defects found during the testing lifecycle of the application