## Sheet1
Schedule | Expected Completion Date | Final Date of Completion | Actual Completion Date | Due Date | Key
|  |  |  | 2024-11-27 | Ahead of Schedule
1. Requirement Analysis | 2024-11-20 | 2024-11-20 |  |  | Target Met
A. Requirements Traceability Matrix updated | 2024-11-20 | 2024-11-20 | 2024-11-20 |  | Target Missed
B. Test Schedule updated | 2024-11-20 | 2024-11-20 | 2024-11-20 |  | Target in Progress
C. Acceptance Criteria updated | 2024-11-20 | 2024-11-20 | 2024-11-20 |  | Document is Fluid
D. Test Results aggregated |  |  | 2024-11-20
2. Test Planning | 2024-11-20 | 2024-11-20 |  | 2024-11-27
A. Integration and unit testing Strategy | 2024-11-20 | 2024-11-20 | 2024-11-20
B. Test Plan is updated | 2024-11-20 | 2024-11-20 | 2024-11-20
3. Test Case Development | 2024-11-21 | 2024-11-21 |  | 2024-11-27
A. Automated Test cases | 2024-11-21 | 2024-11-21
B. Test Data | 2024-11-21 | 2024-11-21
C. Setup | 2024-11-21 | 2024-11-21
4. Test Environment Setup | 2024-11-21 | 2024-11-21 |  | 2024-11-27
A. Test environement is configured | 2024-11-21 | 2024-11-21
B. Smoke tests all pass | 2024-11-21 | 2024-11-21
5. Test Execution | 2024-11-25 | 2024-11-14 |  | 2024-11-27
A. Automated integrationand unit Test cases | 2024-11-25 | 2024-11-26
B. Defects are logged in Jira | 2024-11-25 | 2024-11-26
C. Test results are documented in Jira | 2024-11-25 | 2024-11-26
D. Test reports are made | 2024-11-25 | 2024-11-26
6. Test Cycle Closure | 2024-11-26 | 2024-11-26 |  | 2024-11-27
A. Test summary report is made | 2024-11-26 | 2024-11-26
B. Presentation | 2024-11-26 | 2024-11-26
C. Documentation updated | 2024-11-26 | 2024-11-26